# Project Progress Tracking Form

IS52018C Software Projects 2017

|  |  |
| --- | --- |
| **Project Name** | InteriAR |
| **Project Number** | 1 |
| **Document Start Date** | 10/10/2017 |
| **Business Plan Objective** | Interior design app using augmented reality. Also links users to decorators to implement the design. |
| **Sponsor/Supervisor** | Professor Frederic Fol Leymarie |
| **Project Manager** | Cleon Grant |

|  |  |  |
| --- | --- | --- |
| **Budget/hrs** |  | |
| Resource Name | | Budget/hrs |
| Ethan’s time | | 250 |
| Cleon’s time | | 250 |
| Tanzum’s time | | 250 |
| Ifrah’s time | | 250 |
| Liban’s time | | 250 |
| Jibril’s time | | 250 |
| Shah’s time | | 250 |

**Objective/Scope**

1. To brainstorm ideas
2. To decide on a concept and discuss details, think about stakeholders etc. Also meet supervisor.
3. Discuss personas and diagrams.
4. Create persona template.
5. Revaluate core ideas of the app after research into concerns, discuss with supervisor.
6. Create personas.
7. Create user requirements documents.
8. Meeting to update group on individual work done.
9. Create Functional Architecture Diagram.
10. Create Use Case Diagram.
11. Create Stakeholder Diagram.
12. Create Activity Diagram.
13. Market Research.
14. Create Sequence Diagrams.
15. Design conceptual prototype.
16. Meet to consolidate diagrams etc.
17. Research feasibility, AR libraries etc.
18. Meet to delegate tasks and consolidate work.
19. Research potential user hubs (forums etc.)
20. Work breakdown and critical path
21. Create Gantt chart.
22. Meet for lab and to discuss work done over R/W.
23. Functional prototypes.
24. Group meeting plus supervisor meeting
25. Email stakeholders
26. Group meeting
27. Compile project proposal
28. Technical specification
29. Database prototyping
30. Finalising conceptual statement and stakeholder emails
31. Meeting for proposal
32. Create poster and prep for fair
33. Preliminary backlog
34. Meeting to set scrum times, initial sprint backlog
35. Importing 3D objects into app and tracking testing
36. Facebook/Google login api doc
37. Pop up menu with object buttons

**Status/Progress**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | Task ID | Status | Resources used: Name & hrs |
| 10/10/17 | 1 | Complete | Full group – 1.5 hours each |
| 17/10/17 | 2 | Complete | Full group – 3 hours ea. |
| 19/10/17 | 3 | Complete | Full group – 1h ea. |
| 21/10/17 | 4 | Complete | Ethan 0.5h |
| 24/10/17 | 5 | Complete | Full group 2h ea. |
| 25/10/17 | 6 | Complete | Ethan 2h |
| 26/10/17 | 8 | Complete | E,C,I,J,S,L – 1h |
| 29/10/17 | 7 | Complete | Ethan 2h |
| 30/10/17 | 9 | Complete | Cleon 2h |
| 31/10/17 | 10 | Complete | Cleon 1h |
| 31/10/17 | 11 | Complete | Liban 1.5h |
| 31/10/17 | 12 | Complete | Shah 4h |
| 31/10/17 | 13 | Complete (for now, more to do later) | Ifrah 5h |
| 03/11/17 | 14 | Complete | Jibril 4h |
| 31/10/17 | 15 | Complete | J,S – 7.5h |
| 31/10/17 | 16 | Complete | E,C,I,J,S – 2h, L - 0.5H |
| 17/11/17 | 17 | Complete | E,C – 6h |
| 02/11/17 | 18 | Complete | E,C,I,J,T,L - 1h |
| 11/11/17 | 19 | Complete | Tanzum 2h |
| 11/11/17 | 20 | Complete | L – 6h E – 0.5h |
| 14/11/17 | 21 | Complete | Ethan 2h |
| 14/11/17 | 22 | Complete | E,C,L,J,T,S - 2h, I 1h |
| 20/11/17 | 23 | Complete | E - 8h C – 3h |
| 21/11/17 | 24 | Complete | Full group – 2h |
| 15/11/17 | 25 | Complete | Tanzum – 4hr E 0.25h |
| 23/11/17 | 26 | Complete | Full group 0.5h |
| 21/11/17 | 27 | Complete | E -?h, C -?h, I - ?h, T - ?h,  J - ?h, L - ?h, S -?h |
| 28/11/17 | 28 | Not started |  |
| 29/11/17 | 29 | Complete | Ethan – 2.5h |
| 31/11/19 | 30 | Complete | Tanzum 2hr |
| 12/12/2017 | 31 | Complete | E,C,T,I,J 2.5hr L,S – 1.5 |
| 10/01/18 | 32 | Complete | E,C,T,J,L,I – 2.5h |
| 11/01/18 | 33 | Complete | E,C,J – 0.5h |
| 16/01/18 | 34 | Complete | E,C,J,T,S,I 1.5h L - 0.5h |
| 17/01/18 | 35 | Complete | Ethan 4h, Tanzum 1hr |
| 18/01/18 | 36 | In Progress | Tanzum 1hr |
| 24/01/18 | 37 | In Progress | Ethan 1h |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

**Milestone Revision Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| Milestone ID | Revision Plan, including budget revision | Existing Milestone Date | Revised Milestone Date |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Cumulative Resource Usage/hrs CURRENTLY OUTDATED, tally up later** | | | |
| Resource Name | Hrs Used | Hrs Remaining | Revision Date |
| Ethan’s time | 41 |  |  |
| Cleon’s time | 27.5 |  |  |
| Tanzum’s time | 24.5 |  |  |
| Ifrah’s time | 22.5 |  |  |
| Liban’s time | 19.5 |  |  |
| Jibril’s time | 22.5 |  |  |
| Shah’s time | 20.5 |  |  |