# Project Progress Tracking Form

IS52018C Software Projects 2017

|  |  |
| --- | --- |
| **Project Name** | InteriAR |
| **Project Number** | 1 |
| **Document Start Date** | 10/10/2017 |
| **Business Plan Objective** | Interior design app using augmented reality. Also links users to decorators to implement the design. |
| **Sponsor/Supervisor** | Professor Frederic Fol Leymarie |
| **Project Manager** | Cleon Grant |

|  |  |  |
| --- | --- | --- |
| **Budget/hrs** |  | |
| Resource Name | | Budget/hrs |
| Ethan’s time | | 250 |
| Cleon’s time | | 250 |
| Tanzum’s time | | 250 |
| Ifrah’s time | | 250 |
| Liban’s time | | 250 |
| Jibril’s time | | 250 |
| Shah’s time | | 250 |

**Objective/Scope**

1. To brainstorm ideas
2. To decide on a concept and discuss details, think about stakeholders etc. Also meet supervisor.
3. Discuss personas and diagrams.
4. Create persona template.
5. Revaluate core ideas of the app after research into concerns, discuss with supervisor.
6. Create personas.
7. Create user requirements documents.
8. Meeting to update group on individual work done.
9. Create Functional Architecture Diagram.
10. Create Use Case Diagram.
11. Create Stakeholder Diagram.
12. Create Activity Diagram.
13. Market Research.
14. Create Sequence Diagrams.
15. Design conceptual prototype.
16. Meet to consolidate diagrams etc.
17. Research feasibility, AR libraries etc.
18. Meet to delegate tasks and consolidate work.
19. Research potential user hubs (forums etc.)
20. Work breakdown diagram.
21. Create Gantt chart.
22. Meet for lab and to discuss work done over R/W.
23. Functional prototypes.
24. Group meeting plus supervisor meeting

**Status/Progress**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | Task ID | Status | Resources used: Name & hrs |
| 10/10/17 | 1 | Complete | Full group – 1.5 hours each |
| 17/10/17 | 2 | Complete | Full group – 3 hours ea. |
| 19/10/17 | 3 | Complete | Full group – 1h ea. |
| 21/10/17 | 4 | Complete | Ethan 0.5h |
| 24/10/17 | 5 | Complete | Full group 2h ea. |
| 25/10/17 | 6 | Complete | Ethan 2h |
| 26/10/17 | 8 | Complete | E,C,I,J,S,L – 1h |
| 29/10/17 | 7 | Complete | Ethan 2h |
| 30/10/17 | 9 | Complete | Cleon 2h |
| 31/10/17 | 10 | Complete | Cleon 1h |
| 31/10/17 | 11 | Complete | Liban 1.5h |
| 31/10/17 | 12 | Complete | Shah 4h |
| 31/10/17 | 13 | Complete (for now, more to do later) | Ifrah 5h |
| 03/11/17 | 14 | Complete | Jibril 4h |
| 31/10/17 | 15 | In Progress | J,S - ?h |
| 31/10/17 | 16 | Complete | E,C,I,J,S – 2h, L - 0.5H |
| 17/11/17 | 17 | In progress | E,C – 4h |
| 02/11/17 | 18 | Complete | E,C,I,J,T,L - 1h |
| 11/11/17 | 19 | In progress (browsing potential users on forums) | Tanzum 1h |
| 11/11/17 | 20 | In progress (later tasks to be added) | Liban 2h |
| 14/11/17 | 21 | In progress (waiting on critical path diagram) | Ethan 0.5h |
| 14/11/17 | 22 | Complete | E,C,L,J,T,S - 2h, I 1h |
| 20/11/17 | 23 | In Progress (working out feasibility) | E - 4.5h C – 3h |
| 21/11/17 | 24 | Complete | Full group – 2h |
|  |  |  |  |
|  |  |  |  |

**Milestone Revision Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| Milestone ID | Revision Plan, including budget revision | Existing Milestone Date | Revised Milestone Date |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Cumulative Resource Usage/hrs CURRENTLY OUTDATED, tally up later** | | | |
| Resource Name | Hrs Used | Hrs Remaining | Revision Date |
| Ethan’s time | 29 |  |  |
| Cleon’s time | 24.5 |  |  |
| Tanzum’s time | 13.5 |  |  |
| Ifrah’s time | 19.5 |  |  |
| Liban’s time | 17.5 |  |  |
| Jibril’s time | 19.5 |  |  |
| Shah’s time | 18.5 |  |  |